## Product Backlog
APPENDIX XI: Product and Sprint Backlogs
Agile Software Engineering: -Product Backlog
r |  | I want to be able to... | so that... | Notes | Acceptance tests | Priority | Complexity | Status | Return on Investment
1 | System manager | log in using my staff Id and password |  |  | - User Must Login - User Must use correct Login credentials - User Must be loged in as a system manager | 7 | 5 | Completed | 1.4
2 | System manager | upload student data from file |  | - the csv file should have it data arranged in colums appropriately | - Cannot upload an empty file - Must be a .csv .pdf file - Must complete the form wihout an empty field | 10 | 3 | Completed | 3.3333
3 | System manager | input student data |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 6 | 3 | Uncompleted | 2
4 | System manager | view student record that I have input/import |  | could search the list | -user can view student records | 10 | 5 | Completed | 2
5 | System manager | edit student record I have input/import |  |  | - user can edit student records from list of students | 7 | 2 | Completed | 3.5
6 | System manager | upload courses from file |  |  | - Cannot upload an empty file - Must be a .csv .pdf file - Must complete the form wihout an empty field | 4 | 2 | Completed | 2
7 | System manager | input courses data |  |  | - Must cmplete all fields on the form - Cannot submit existing course | 7 | 2 | Completed | 3.5
8 | System manager | view courses I input/import |  | could search the list | -user can view courses | 2 | 1 | Completed | 2
9 | System manager | edit courses I input/import |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 2 | 3 | Completed | 0.66667
10 | System manager | create departments |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 9 | 3 | Completed | 3
11 | System manager | create programmes |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 3 | 2 | Completed | 1.5
12 | System manager | create schools |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 6 | 2 | Completed | 3
13 | System manager | create colleges |  |  | - Must cmplete all fields on the form - Cannot submit existing student records | 3 | 8 | Completed | 0.375
15 | System manager | edit departmnets I have created |  |  | - User can review exams | 7 | 2 | Completed | 3.5
16 | System manager | edit programmes I have created |  |  | - User can add comments as a seperate file | 8 | 8 | Completed | 1
17 | System manager | create backups |  | can be in .sql format | - User can create backups of all record | 3 | 3 | Completed | 1
17 | System manager | create users / staff | they have accounts/profiles | user account will be created and password is set | - User can import backups | 3 | 3 | Completed | 1
17 | System manager | Edit user account | they can be denied access | can reset user login details | - User can edit user login details | 3 | 3 | Completed | 1
49 | System manager | oversee all accounts |  | Some accounts could be stdents accounts. | - Admin must see a table with all account information | 9 | 2 | Completed | 4.5
19 | Exam officer | log in using my staff Id and password |  |  | - User Must Login - User Must use their Login credentials - User Must be loged in as an exam officer | 7 | 5 | Completed | 1.4
20 | Exam officer | import exam scores |  | Could be uploaded course by course | - Cannot upload an empty file - Must be a .csv file - Must complete the form wihout an empty field | 5 | 2 | Completed | 2.5
| Exam officer | input exam scores |  |  | - Cannot upload an empty file - Must complete the form wihout an empty field | 5 | 2 | Completed | 2.5
Exam officer
21 | Exam officer | view result broadsheet in academic board format |  |  | - User must be logged in as an Exam Officer - User can view, print download the files | 2 | 2 | Completed | 1
| Exam officer | view result broadsheet in notice board format | [5 empty] | Completed
| Exam officer | consider student score |  | could be based on an agrreed score | -score must be the aggreed score | 3 | 3 | Completed | 1
| Exam officer | allocate courses to staff |  | could show list of allocation | - no field can be submitted empty - | 3 | 2 | Completed | 1.5
| Exam officer | reset allocation |  |  | - must reset staff allocated | 3 | 2 | Completed | 1.5
| Exam & records | view result analysis |  | could specify a department/course | -user can view result analysis | 4 | 3 | Completed | 1.3333
| Exam officer | delete exam scores |  |  |  | 2 | 2 | Completed | 1
| Exam officer | change my login details |  |  | - must be logged in - must comfirmation password -not empty fields cann be submitted | 3 | 2 | Completed | 1.5
23 | Student | log in using my matric numberpassword |  |  | - User Must Login - User Must use correct Login credentials - User Must be loged in as a Student | 7 | 5 | Completed | 1.4
24 | Student | view all semeter results |  |  | -user can view all semester results | 2 | 2 | Completed | 1
25 | Student | view specific semester result |  |  | -user can view a specific semester result | 2 | 2 | Completed | 1
26 | Student | change my login details |  |  | - must be logged in - must comfirmation password -not empty fields cann be submitted | 3 | 2 | Completed | 1.5
32
33 | Teaching Staff | login with my staff Id and password |  |  | - must use the credentials given for guest accounts - must be a User, thats assigned to the system (no unauthorised access) | 7 | 5 | Completed | 1.4
34 | Teaching Staff | upload exam scores |  |  | - Cannot upload an empty file - Can only upolad scores for courses allocated - Must be a .csv .pdf file - Must complete the form wihout an empty field | 3 | 2 | Completed | 1.5
35 | Teaching Staff | view the scores I uploaded |  |  | - user can view only scores uploaded | 7 | 2 | Completed | 3.5
36 | Teaching Staff | change my login details |  |  | - must be logged in - must comfirmation password -not empty fields cann be submitted | 8 | 8 | Completed | 1
41
.
42 | Exam & records | login with my staff Id and password |  |  | - Must us the credentials given for guest accounts - Must be a user, thats assigned to the system (no unauthorised access) | 7 | 5 | Completed | 1.4
43 | Exam & records | view list of student |  | could specify a department, could search the list | -user can view student records | 4 | 4 | Completed | 1
| Exam & records | view list of courses |  | could specify a department, could search the list | -user can view list of courses | 5 | 3 | Completed | 1.6667
| Exam & records | view academic board results |  | could specify a department | -user can view broad sheets result in academic board format | 5 | 3 | Completed | 1.6667
| Exam & records | view result analysis |  | could specify a department/course | -user can view result analysis | 4 | 3 | Completed | 1.3333
44 | Exam & records | change my login details |  |  | - must be logged in - must comfirmation password -not empty fields cann be submitted | 7 | 3 | Completed | 2.3333
57 | Developer | Support excell .csv |  |  | - Only allows .CSV file - Warnings must use allowed formats | 4 | 3 | Completed | 1.3333
58 | Developer | Test for browser compatibility |  |  | - Test common browsers | 3 | 8 | Completed | 0.375
59 | Developer | Work on all browsers |  |  | - Website must work on all browser difference - Website must run on newest versions | 3 | 1 | Completed | 3
60 | Developer | keep previous exams records |  |  | - Must store previous exam scores - no score Must be deleted - Previous result Must be accessible to Exam officer and exams and record | 3 | 3 | Completed | 1
Agile Software Engineering - Sprint Backlogs - Sprint 1 - 5
| User Story | Estimated Complexity | Done? | Tasks | Estimated Effort | Mon | Tue | Wed | Thu | Fri
Sprint 1
| 1. Spike .csv file format upload to MYSQL | 4 | Y | Spike | 2 | 0 | 2 | 1 | 0 | 1
| 2. As System manager, upload student records | 1 | Y | Create HTML upload form | 1 | 0 | 1 | 0 | 0 | 1
|  | 2 | Y | Upload student record into database from file | 6 | 0 | 2 | 0 | 3 | 1
|  | 5 | Y | Set up database structure | [5 empty] | 0
| 3. As System manager, upload courses | 2 | Y | Create HTML upload form | 3 | 0 | 0 | 1 | 4 | 1
|  | 2 | Y | Upload courses into database from file | [5 empty] | 0
| 4. As System manager, create users | 2 | Y | Create form to add accounts, implement the add function | 5 | 0 | 2 | 2 | 1 | 1
| 5. As system manager, create programmes | 1 | Y | Create HTML forms | 5 | 0 | 2 | 3 | 3 | 1
|  | 3 | Y | Add programmes to database | [5 empty] | 0
|  | 1 | Y | Add department to database | 1 | 0 | 1 | 1 | 0 | 1
|  | 1 | Y | Add school to database | 4 | 0 | 2 | 2 | 1 | 0
|  | 1 | Y | Add colleges to database | [5 empty] | 1
[5 empty] | 3 | 0 | 0 | 3 | 1 | 0
| 6. As exam officer upload exams score | 1 | Y | Create HTML form | [5 empty] | 0
|  | 4 | Y | Upload scores into database | 1 | 0 | 1 | 0 | 0 | 1
|  |  | Y |  | 1 | 0 | 1 | 0 | 0 | 1
| 7. As a teaching staff, upload exam score | 1 | Y | Create HTML upload form | 1 | 0 | 1 | 0 | 0 | 1
|  | 2 | Y | Upload scores into database | [5 empty] | 1
|  | 3 | Y | Display the Scores uploaded | 6 | 0 | 3 | 2 | 1 | 1
Sprint 2
| 1. create login for all user type | 1 | Y | Create form | 3 | 0 | 2 | 0 | 0 | 2
|  | 3 | Y | Connect to database to check | 3 | 0 | 2 | 3 | 0 | 0
|  | 1 | Y | Set session | 3 | 0 | 2 | 0 | 0 | 1
|  | 3 | Y | Hash user password | 3 | 0 | 3 | 0 | 0 | 0
|  | 1 | Y | Verify user hashed password | 3 | 0 | 2 | 0 | 0 | 0
[5 empty] | 3 | 0 | 2 | 0 | 0 | 2
| 2. Spike Bcrypt password hash and verify | 4 | Y | spike | 3 | 0 | 0 | 0 | 0 | 0
| 3. As system manager, input student record | 1 | Y | Create HTML form | 1 | 0 | 0 | 0 | 0 | 1
|  | 1 | Y | Add records to database | 6 | 0 | 2 | 3 | 6 | 0
| 5. As exam officer, view broadsheet | 1 | Y | Create HTML Table | 1 | 0 | 2 | 1 | 0 | 1
|  | 7 | Y | Map score to grade | 5 | 0 | 2 | 3 | 3 | 1
|  | 6 | Y | Map score to point | 1 | 0 | 1 | 0 | 0 | 0
|  | 4 | Y | Generate GPA, CGPA | 6 | 0 | 2 | 3 | 3 | 1
|  | 5 | Y | Create remarks | 5 | 0 | 2 | 3 | 3 | 1
|  | 8 | Y | Implement Academic broadsheet result | 5 | 0 | 3 | 1 | 1 | 0
| 6. As system manager, create backup | 4 | Y | Create backup | 5 | 0 | 2 | 3 | 3 | 1
|  | 4 | Y | Import backup | 1 | 0 | 1 | 1 | 0 | 1
| 7. As Student, view my semester result | 1 | Y | Create html formatted page | 3 | 0 | 0 |  |  | 0
|  | 4 | Y | View student semester result | 5 | 0 | 2 | 3 | 3 | 1
Sprint 3
| 1. Allocate course | 2 | Y | View all department courses | 1 | 0 | 1 | 1 | 0 | 0
|  | 3 | Y | Choose and allocate course to staff | 4 | 0 | 2 | 2 | 1 | 1
| 2. Spike web visualisation API | 8 | Y | spike | 3 | 0 | 0 | 3 | 1 | 0
| 3. As exams & record, View result analysis | 2 | Y | Create table | 1 | 0 | 3 | 3 | 3 | 1
|  | 4 | Y | View analysis by grade in table result | 1 | 0 | 2 | 3 | 3 | 1
|  | 4 | Y | View analysis summary in table | 1 | 0 | 1 | 0 | 0 | 1
|  | 6 | Y | View visualise analysis | 1 | 0 | 1 | 0 | 0 | 0
|  | 8 | N | Visualise analysis comparing semesters | 1 | 0 | 1 | 0 | 0 | 1
| 4. As System manager, control user menu | 3 | Y | View all user menu | 4 | 0 | 3 | 2 | 1 | 1
|  | 3 | Y | Disable and enable user menu | 3 | 0 | 2 | 0 | 0 | 2
| 5. Form validation | 4 | Y | Validate user input, strip unwanted xters. | 3 | 0 | 2 | 0 | 0 | 1
| 6. Upload CSV format | 4 | Y | Ensure file format is .csv | 3 | 0 | 2 | 3 | 0 | 1
[5 empty] | 3 | 0 | 2 | 0 | 0 | 1
| 7. User logs | 5 | Y | Create user logs for input, edit, and logins | 3 | 0 | 3 | 0 | 0 | 1
Sprint 4
| 1. Single course analysis | 4 | Y | Visualise analysis of single course | [5 empty] | 1
| 2. As System manager, view student | 1 | Y | Make a page with a table | [5 empty] | 0
|  | 2 | Y | View student records | 2 | 0 | 0 | 0 | 0 | 1
| 3. As System manager, view courses | 1 | Y | Make a page with a table | [5 empty] | 0
|  | 2 | Y | View courses | 2 | 0 | 2 | 1 | 0 | 1
| 4. As system manager, modify user access | 2 | Y | View user | 1 | 0 | 1 | 0 | 0 | 1
|  | 3 | Y | Modify user account | 3 | 0 | 2 | 3 | 3 | 0
| 5. As system manager, modify programme | 2 | Y | View programmes | 5 | 0 | 3 | 1 | 1 | 0
| 6. As system manager, generate file format | 3 | Y | Course upload .csv file format | [5 empty] | 0
|  | 2 | Y | Student upload .csv file format | 1 | 0 | 1 | 1 | 0 | 1
|  | 1 | Y | Ensure the require data is uploaded | 5 | 0 | 2 | 2 | 1 | 1
Sprint 5
| 1. As Exam officer, generate file format | 2 | Y | Score upload .csv file format
| 2. Change all user login detail | 1 | Y | Compare old user detail to new | 1 | 0 | 1 | 1 | 0 | 0
| 3. As System manager, view all user | 1 | Y | Make a page with table | 3 | 0 | 0 | 3 | 1 | 1
| 4. Create user views | 4 | Y | Create user views with different menus | 1 | 0 | 3 | 3 | 3 | 0
| 5. Logout | 2 | Y | Live page and destroy all sessions | 1 | 0 | 1 | 0 | 0 | 0
| 6. Export files to word | 4 | Y | Implement result export to word | 1 | 0 | 1 | 0 | 0 | 0
| 7. Export file to PDF | 4 | N | Implement result export to PDF | 1 | 0 | 1 | 0 | 0 | 0
|  | 6 | N | Compare Visual Analysis Yearly | 1 | 0 | 1 | 0 | 0 | 0
[6 empty] | Not started | In progress | Completed
| Estimated velocity | 164 |  | Effort remaining | 164 | 0 | 94 | 71 | 54 | 45

## Sheet1
Agile Software Engineering - Sprint BAcklogs - Sprint 1 - 5
User Story | Estimated Complexity | Done? | Tasks | Estimated Effort | Mon | Tue | Wed | Thu | Fri
Sprint 1
1. Spike .csv file format upload to MYSQL | 4 |  | Spike | 2 | 0 | 2 | 1 | 0 | 1
2. As System manager, upload student records | 1 | Y | Create HTML upload form | 1 | 0 | 1 | 0 | 0 | 1
| 2 |  | Upload student record into database from file | 6 | 0 | 2 | 0 | 3 | 1
| 5 |  | Set up database structure | [5 empty] | 0
3. As System manager, upload courses | 2 | Y | Create HTML upload form | 3 | 0 | 0 | 1 | 4 | 1
| 2 |  | Upload courses into database from file | [5 empty] | 0
4. As System manager, create users | 2 | Y | Create form to add accounts, implement the add function | 5 | 0 | 2 | 2 | 1 | 1
5. As system manager, create programmes | 1 | Y | Create HTML forms | 5 | 0 | 2 | 3 | 3 | 1
| 3 | Y | Add programmes to database | [5 empty] | 0
| 1 | Y | Add department to database | 1 | 0 | 1 | 1 | 0 | 1
| 1 | Y | Add school to database | 4 | 0 | 2 | 2 | 1 | 0
| 1 | Y | Add colleges to database | [5 empty] | 1
|  |  |  | 3 | 0 | 0 | 3 | 1 | 0
6. As exam officer upload exams score | 1 | Y | Create HTML form | [5 empty] | 0
| 4 | Y | Upload scores into database | 1 | 0 | 1 | 0 | 0 | 1
|  | Y |  | 1 | 0 | 1 | 0 | 0 | 1
7. As a teaching staff, upload exam score | 1 | Y | Create HTML upload form | 1 | 0 | 1 | 0 | 0 | 1
| 2 | Y | Upload scores into database | [5 empty] | 1
| 3 | Y | Display the Scores uploaded | 6 | 0 | 3 | 2 | 1 | 1
Sprint 2
1. create login for all user type | 1 | Y | Create form | 3 | 0 | 2 | 0 | 0 | 2
| 3 | Y | Connect to database to check | 3 | 0 | 2 | 3 | 0 | 0
| 1 | Y | Set session | 3 | 0 | 2 | 0 | 0 | 1
| 3 | Y | Hash user password | 3 | 0 | 3 | 0 | 0 | 0
| 1 | Y | Verify user hashed password | 3 | 0 | 2 | 0 | 0 | 0
|  |  |  | 3 | 0 | 2 | 0 | 0 | 2
2. Spike Bcrypt password hash and verify | 4 | Y | spike | 3 | 0 | 0 | 0 | 0 | 0
3. As system manager, input student record | 1 | Y | Create HTML form | 1 | 0 | 0 | 0 | 0 | 1
| 1 | Y | Add records to database | 6 | 0 | 2 | 3 | 6 | 0
5. As exam officer, view broadsheet | 1 | Y | Create HTML Table | 1 | 0 | 2 | 1 | 0 | 1
| 7 |  | Map score to grade | 5 | 0 | 2 | 3 | 3 | 1
| 6 |  | Map score to point | 1 | 0 | 1 | 0 | 0 | 0
| 4 |  | Generate GPA, CGPA | 6 | 0 | 2 | 3 | 3 | 1
| 5 |  | Create remarks | 5 | 0 | 2 | 3 | 3 | 1
| 8 | Y | Implement Academic broadsheet result | 5 | 0 | 3 | 1 | 1 | 0
6. As system manager, create backup | 4 | Y | Create backup | 5 | 0 | 2 | 3 | 3 | 1
| 4 | Y | Import backup | 1 | 0 | 1 | 1 | 0 | 1
7. As Student, view my semester result | 1 | Y | Create html formatted page | 3 | 0 | 0 |  |  | 0
| 4 | Y | View student semester result | 5 | 0 | 2 | 3 | 3 | 1
Sprint 3
1. Allocate course | 2 | Y | View all department courses | 1 | 0 | 1 | 1 | 0 | 0
| 3 | Y | Choose and allocate course to staff | 4 | 0 | 2 | 2 | 1 | 1
2. Spike web visualisation API | 8 | Y | spike | 3 | 0 | 0 | 3 | 1 | 0
3. As exams & record, View result analysis | 2 | Y | Create table | 1 | 0 | 3 | 3 | 3 | 1
| 4 | Y | View analysis by grade in table result | 1 | 0 | 2 | 3 | 3 | 1
| 4 | Y | View analysis summary in table | 1 | 0 | 1 | 0 | 0 | 1
| 6 | Y | View visualise analysis | 1 | 0 | 1 | 0 | 0 | 0
| 8 | N | Visualise analysis comparing semesters | 1 | 0 | 1 | 0 | 0 | 1
4. As System manager, control user menu | 3 | Y | View all user menu | 4 | 0 | 3 | 2 | 1 | 1
| 3 | Y | Disable and enable user menu | 3 | 0 | 2 | 0 | 0 | 2
5. Form validation | 4 | Y | Validate user input, strip unwanted xters. | 3 | 0 | 2 | 0 | 0 | 1
6. Upload CSV format | 4 | Y | Ensure file format is .csv | 3 | 0 | 2 | 3 | 0 | 1
|  |  |  | 3 | 0 | 2 | 0 | 0 | 1
7. User logs | 5 | Y | Create user logs for input, edit, and logins | 3 | 0 | 3 | 0 | 0 | 1
|  |  |  | 3 | 0 | 2 | 0 | 0 | 1
Sprint 4 |  |  |  | 3 | 0 | 2 | 0 | 0 | 0
1. Single course analysis | 4 | Y | Visualise analysis of single course | [5 empty] | 1
2. As System manager, view student | 1 | Y | Make a page with a table | [5 empty] | 0
| 2 | Y | View student records | 2 | 0 | 0 | 0 | 0 | 1
3. As System manager, view courses | 1 | Y | Make a page with a table | [5 empty] | 0
| 2 |  | View courses | 2 | 0 | 2 | 1 | 0 | 1
4. As system manager, modify user access | 2 | Y | View user | 1 | 0 | 1 | 0 | 0 | 1
| 3 |  | Modify user account | 3 | 0 | 2 | 3 | 3 | 0
5. As system manager, modify programme | 2 | Y | View programmes | 5 | 0 | 3 | 1 | 1 | 0
6. As system manager, generate file format | 3 | Y | Course upload .csv file format | [5 empty] | 0
| 2 | Y | Student upload .csv file format | 1 | 0 | 1 | 1 | 0 | 1
| 1 | Y | Ensure the require data is uploaded | 5 | 0 | 2 | 2 | 1 | 1
Sprint 5
1. As Exam officer, generate file format | 2 | Y | Score upload .csv file format
2. Change all user login detail | 1 | Y | Compare old user detail to new | 1 | 0 | 1 | 1 | 0 | 0
0
3. As System manager, view all user | 1 | Y | Make a page with table | 3 | 0 | 0 | 3 | 1 | 1
4. Create user views | 4 | Y | Create user views with different menus | 1 | 0 | 3 | 3 | 3 | 0
5. Logout | 2 | Y | Live page and destroy all sessions | 1 | 0 | 1 | 0 | 0 | 0
6. Export files to word | 4 | Y | Implement result export to word | 1 | 0 | 1 | 0 | 0 | 0
7. Export file to PDF | 4 | N | Implement result export to PDF | 1 | 0 | 1 | 0 | 0 | 0
| 6 | N | Compare Visual Analysis Yearly | 1 | 0 | 1 | 0 | 0 | 0
[7 empty] | Not started | In progress | Completed
Estimated velocity | 170 |  | Effort remaining | 170 | 0 | 98 | 71 | 54 | 46
Actual velocity | 269
1